## Product Backlog
THE APPLICATION DEVELOPMENT PROJECT TOPIC
PRODUCT BACKLOG
Function Name | Feature | Complexity | Planned Code Iteration | In-charge Roll Number | In-charge Full Name | Actual Code Iteration
Sign up | Public | Medium | Iteration 1 |  | Truong
Sign in | Public | Simple | Iteration 1 |  | Thien
View profile-cv of mentor | Public | Medium | Iteration 1 |  | Phu
View all skills | Public | Simple | Iteration 1 |  | Quyen
Change Password | Common | Simple | Iteration 1 |  | Tri
Reset Password | Common | Medium | Iteration 1 |  | Tin
User Authorization | Common | Complex | Iteration 1 |  | Truong
View list all mentor | Admin | Complex | Iteration 1 |  | Thien
View list following Request | Mentor | Simple | Iteration 2 |  | Phu
List of inviting request | Mentor | Simple | Iteration 2 |  | Quyen
Create CV of mentor | Mentor | Medium | Iteration 2 |  | Tri
Update CV of mentor | Mentor | Medium | Iteration 2 |  | Tin
Update Mentee profile | Mentee | Simple | Iteration 2 |  | Truong
Rate & comment mentor | Mentee | Simple | Iteration 2 |  | Thien
Statistic of all mentee | Admin | Simple | Iteration 2 |  | Phu
View list of skills | Admin | Medium | Iteration 2 |  | Quyen
Create skill | Admin | Simple | Iteration 2 |  | Tri
Update skill | Admin | Simple | Iteration 2 |  | Tin
View statistic request | Mentor | Complex | Iteration 3 |  | Truong
Create request | Mentee | Medium | Iteration 3 |  | Thien
List request by me | Mentee | Medium | Iteration 3 |  | Phu
Statistic request by me | Mentee | Simple | Iteration 3 |  | Quyen
Update request | Mentee | Medium | Iteration 3 |  | Tri
List Mentor suggestion (for Mentee) | Mentee | Complex | Iteration 3 |  | Tin
View list all request | Admin | Complex | Iteration 3 |  | Truong