## Product Backlog
THE APPLICATION DEVELOPMENT PROJECT TOPIC
PRODUCT BACKLOG
Function Name | Feature | Complexity | Planned Code Iteration | In-charge Roll Number | In-charge Full Name | Actual Code Iteration
Sign in | Public | Simple | Iteration 1 | SE160467 | Lê Nam Phú
View all skills | Public | Simple | Iteration 1 | SE160486 | Lê Trí Quyền
Sign up | Public | Medium | Iteration 1 | SE140486 | Trần Quốc Trí
View profile-cv of mentor | Public | Medium | Iteration 1 | SE160518 | Nguyễn Đăng Trường
Change Password | Common | Simple | Iteration 1 | SE141165 | Đỗ Trọng Tín
Reset Password | Common | Medium | Iteration 1 | SE141165 | Đỗ Trọng Tín
User Authorization | Common | Complex | Iteration 1 | SE160518 | Nguyễn Đăng Trường
View list all mentor | Admin | Complex | Iteration 1 | SE141165 | Đỗ Trọng Tín
View list following Request | Mentor | Simple | Iteration 2 | SE160518 | Nguyễn Đăng Trường
List of inviting request | Mentor | Simple | Iteration 2 | SE150336 | Trần Lê Phúc Thiện
Create CV of mentor | Mentor | Medium | Iteration 2 | SE150336 | Trần Lê Phúc Thiện
Update CV of mentor | Mentor | Medium | Iteration 2 | SE140486 | Trần Quốc Trí
Update Mentee profile | Mentee | Simple | Iteration 2 | SE140486 | Trần Quốc Trí
Rate & comment mentor | Mentee | Simple | Iteration 2 | SE160467 | Lê Nam Phú
Statistic of all mentee | Admin | Simple | Iteration 2 | SE160486 | Lê Trí Quyền
Create skill | Admin | Simple | Iteration 2 | SE160518 | Nguyễn Đăng Trường
Update skill | Admin | Simple | Iteration 2 | SE141165 | Đỗ Trọng Tín
View list of skills | Admin | Medium | Iteration 2 | SE160518 | Nguyễn Đăng Trường
View statistic request | Mentor | Complex | Iteration 3 | SE150336 | Trần Lê Phúc Thiện
Statistic request by me | Mentee | Simple | Iteration 3 | SE150336 | Trần Lê Phúc Thiện
Create request | Mentee | Medium | Iteration 3 | SE141165 | Đỗ Trọng Tín
List request by me | Mentee | Medium | Iteration 3 | SE150336 | Trần Lê Phúc Thiện
Update request | Mentee | Medium | Iteration 3 | SE140486 | Trần Quốc Trí
List Mentor suggestion (for Mentee) | Mentee | Complex | Iteration 3 | SE140486 | Trần Quốc Trí
View list all request | Admin | Complex | Iteration 3 | SE141165 | Đỗ Trọng Tín